## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | CareerAI – AI-Based Career Prediction & Learning Recommendation System
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-06-12
EXPECTED COMPLETION DATE | 2026-08-22
ESTIMATED COST | N.A. – Open-source/free software and existing computing resources
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop an AI-based career prediction prototype that analyses student skills, interests, learning behaviour and work preferences, predicts a suitable job role from the supplied PS2_Dataset.csv dataset, and provides a career-specific learning/course roadmap through an interactive Streamlit application.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Students often need structured guidance when selecting a suitable technical career path. CareerAI provides a single application that combines exploratory data analysis, machine-learning classification, user-profile prediction and course recommendations. The preferred solution is an open-source Python/Streamlit prototype using the teacher-provided dataset, avoiding paid software or APIs.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Primary goals: complete the end-to-end ML workflow; compare multiple classification models; evaluate accuracy, precision, recall and F1 score; integrate the selected best-performing model into a Streamlit UI; accept user profile inputs; display the predicted career role and top career matches; and provide a structured course roadmap. Success is measured by completion of the required project workflow and transparent model evaluation on the supplied dataset.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Clean and prepared PS2_Dataset.csv. 2. EDA outputs including target distribution and feature analysis. 3. Trained and evaluated classification models. 4. Model-comparison results with accuracy, precision, recall and F1 score. 5. Confusion matrix and model-analysis outputs. 6. Streamlit CareerAI application with user input and prediction interface. 7. Career-specific course/learning roadmap module. 8. Project documentation, source code and final report.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Dataset loading and validation; data preprocessing; categorical/numerical feature handling; EDA; stratified train-test evaluation; Decision Tree, Random Forest, Extra Trees and CatBoost model training; model comparison; prediction UI; career-role output; confidence/top-role display where supported; and local career-specific course recommendations.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Paid APIs or paid software; collection of new proprietary datasets; production deployment at enterprise scale; medical/psychological diagnosis; guaranteed career placement; external recruitment integration; live labour-market prediction; and features not required by the supplied project scope.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 primary project resource: Manvith Mogaveera – project development, data preparation, machine learning, evaluation, Streamlit integration, testing and documentation. Project sponsor and manager are as specified in the GPI template.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop/PC; Python 3.x; VS Code/Jupyter or equivalent IDE; Streamlit; Pandas; NumPy; Scikit-learn; Matplotlib; Seaborn; XGBoost; LightGBM; CatBoost; Git/GitHub if required; provided PS2_Dataset.csv; and open-source/free software resources.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N.A. for additional project expenditure. Development is planned using existing computing resources and open-source/free software and libraries. No paid API or commercial software is required for the core prototype.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd. / Global Professional Internship (GPI) project owner
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Cloud Counselage Pvt. Ltd.; GPI/domain leadership; Project Sponsor Tushar Topale; Project Manager Harshada Topale; Manvith Mogaveera as project intern/developer; and relevant GPI/domain stakeholders involved through requirement and weekly meetings.
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd. – Global Professional Internship / Live Project
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Low predictive signal in the supplied dataset may limit model accuracy. 2. Incorrect or ambiguous feature interpretation may affect preprocessing. 3. Model performance may vary across train/test splits. 4. Streamlit/library compatibility or environment issues may affect deployment. 5. Limited time/resources may restrict advanced experimentation.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. The provided PS2_Dataset.csv is the required primary dataset. 2. The supplied target variable is Suggested Job Role with 12 job-role classes. 3. Open-source/free software is sufficient for the prototype. 4. Users provide profile information through the application for prediction. 5. The model's measured performance is accepted as an experimental result and is not artificially inflated.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. Must use the supplied project/domain and dataset unless formally permitted otherwise. 2. Must follow GPI project-management and submission requirements. 3. Must use open-source/free/trial software for the Live Project. 4. No unsupported claim of high accuracy or guaranteed career suitability. 5. Project schedule and final submission dates remain subject to the official GPI schedule.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2026-06-12
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2026-06-20
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-06-30
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-07-20
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 2026-07-31
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 2026-08-07
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-08-22