## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | CareerAI – AI-Based Career Prediction & Learning Recommendation System
PROJECT ID | GPI-CAR-AI-001
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 12-Jun-2026 | Project initiation showed that a clear understanding of the problem statement and expected deliverables was essential before beginning development. | Requirements / Planning | Yes | Break the problem statement into clear objectives, scope, deliverables and acceptance expectations before implementation. | Complete the Project Charter, Requirement Elicitation Questionnaire and SRS before detailed development. | Manvith Mogaveera | Solved | Early documentation made later planning and development more structured.
2 | 20-Jun-2026 | Initial dataset inspection showed that the class distribution was reasonably balanced, but balance alone did not guarantee that the features contained enough information to predict the target career roles. | Data Analysis | Yes | Check both target distribution and feature-target relationships during the initial EDA. | Use mutual information, feature analysis and baseline accuracy before investing heavily in model tuning. | Manvith Mogaveera | Solved | This became one of the most important findings of the project.
3 | 24-Jun-2026 | The dataset contained categorical and numerical attributes that required consistent preprocessing before being supplied to different machine-learning models. | Data Preprocessing | Yes | Separate numerical and categorical features and use a reproducible preprocessing pipeline. | Validate data types, encode categorical variables and maintain the same preprocessing logic for training and prediction. | Manvith Mogaveera | Solved | Consistent preprocessing reduced the risk of train-test inconsistencies.
4 | 08-Jul-2026 | Multiple classification models were required because performance varied between algorithms and no single model could be assumed to be best in advance. | Machine Learning | No | Compare several suitable algorithms using the same train-test split and evaluation criteria. | Train and compare Random Forest, Extra Trees, XGBoost, LightGBM, CatBoost and the neural-network approach. | Manvith Mogaveera | Solved | Model comparison provided a more objective basis for model selection.
5 | 10-Jul-2026 | Model evaluation showed that accuracy remained close to the twelve-class random baseline despite trying different models. | Model Evaluation | Yes | Investigate the information content of the features before relying on additional hyperparameter tuning. | Compare full-feature performance with single-feature, interaction and randomized-label sanity checks and document the limitation. | Manvith Mogaveera | Solved | The result indicated that the limitation was primarily related to the available data rather than the model pipeline.
6 | 13-Jul-2026 | Feature importance and mutual-information analysis helped identify which available attributes contained relatively more signal, even though the overall signal remained weak. | Feature Analysis | No | Use feature analysis as a diagnostic step instead of assuming that every collected attribute contributes equally. | Rank features, inspect the strongest individual attributes and test selected feature combinations. | Manvith Mogaveera | Solved | This helped explain model behaviour and supported transparent reporting.
7 | 18-Jul-2026 | Building the prediction interface after defining the model workflow made it easier to connect user inputs with the same preprocessing and prediction pipeline used during training. | Application Development | No | Design the UI around the final prediction pipeline rather than creating the interface independently. | Create the user profile form, connect it to preprocessing and display the predicted career role with supporting recommendations. | Manvith Mogaveera | Solved | The application was planned as a complete user workflow rather than only a model demonstration.
8 | 28-Jul-2026 | Testing showed that input validation and prediction workflow needed to be considered separately from model accuracy. | Testing | Yes | Test data handling, input validation, prediction output and recommendation output as separate components. | Perform functional testing of the form, preprocessing, prediction and course recommendation workflow. | Manvith Mogaveera | Solved | Separating these checks made it easier to identify whether a problem was in the UI, preprocessing or model.
9 | 07-Aug-2026 | Keeping project documentation alongside development made final reporting and handover easier because decisions, limitations and deliverables were already recorded. | Documentation | No | Maintain documentation continuously instead of preparing the complete report only at the end. | Update the project schedule, RAID log, requirements documents and weekly project records throughout the project. | Manvith Mogaveera | Solved | Continuous documentation reduced the effort required during project closure.
10 | 2026-08-22 | The final handover required the application, source code, model workflow and project documentation to be organised as a complete deliverable rather than as separate development outputs. | Project Closure / Handover | No | Prepare a handover checklist and verify that technical and project-management documents are complete before closure. | Organise the CareerAI application, source code, model and preprocessing workflow, evaluation results and project documents for final stakeholder handover. | Manvith Mogaveera | Solved | The final handover marked the formal completion of the project and provided a clear basis for future improvements.