## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Program 2023 - Artificial Intelligence & Machine Learning Project Schedule
|  | PROJECT NAME | CareerAI – AI-Based Career Prediction & Learning Recommendation System
|  | PROJECT START DATE | 2026-06-12 | (Enter the date you started working on your project)
|  | Display Week Sr No | 1 | [10 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2026-06-08 to 2026-08-09
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2026-06-08 to 2026-08-09
1 Initiation | [10 empty] | COMPLETED | 1 | Completed
| 1.1 Identify business problem | Manvith Mogaveera | 2026-06-12 | 2026-06-13 | 2 | COMPLETED |  | 1900-01-03 | 2026-06-13 | Completed
| 1.2 Define project objective and scope | Manvith Mogaveera | 2026-06-12 | 2026-06-14 | 3 | COMPLETED | 1.1 | 5 | 2026-06-14 | Completed
| 1.3 Create project charter | Manvith Mogaveera | 2026-06-13 | 2026-06-15 | 3 | COMPLETED | 1.2 | 5 | 2026-06-15 | Completed
| 1.4 Requirement elicitation | Manvith Mogaveera | 2026-06-14 | 2026-06-16 | 3 | COMPLETED | 1.2 | 5 | 2026-06-16 | Completed
| 1.5 Prepare Software Requirements Specification | Manvith Mogaveera | 2026-06-15 | 2026-06-18 | 4 | COMPLETED | 1.3, 1.4 | 8 | 2026-06-18 | Completed
2 Planning | [10 empty] | COMPLETED | 1 | Completed
| 2.1 Create Work Breakdown Structure | Manvith Mogaveera | 2026-06-18 | 2026-06-20 | 3 | COMPLETED | 1.5 | 5 | 2026-06-20 | Completed
| 2.2 Baseline project plan and schedule | Manvith Mogaveera | 2026-06-19 | 2026-06-21 | 3 | COMPLETED | 2.1 | 5 | 2026-06-21 | Completed
| 2.3 Identify project risks and dependencies | Manvith Mogaveera | 2026-06-20 | 2026-06-22 | 3 | COMPLETED | 2.1 | 4 | 2026-06-22 | Completed
| 2.4 Inspect teacher-provided PS2_Dataset.csv | Manvith Mogaveera | 2026-06-20 | 2026-06-22 | 3 | COMPLETED | 2.1 | 6 | 2026-06-22 | Completed
| 2.5 Finalize ML, UI and recommendation technology stack | Manvith Mogaveera | 2026-06-21 | 2026-06-23 | 3 | COMPLETED | 2.4 | 4 | 2026-06-23 | Completed
3 Development | [10 empty] | COMPLETED | 1 | Completed
| 3.1 Load and validate dataset | Manvith Mogaveera | 2026-06-23 | 2026-06-24 | 2 | COMPLETED | 2.4 | 1900-01-03 | 2026-06-24 | Completed
| 3.2 Data cleaning and preprocessing | Manvith Mogaveera | 2026-06-23 | 2026-06-27 | 5 | COMPLETED | 3.1 | 1900-01-07 | 2026-06-27 | Completed
| 3.3 Exploratory data analysis | Manvith Mogaveera | 2026-06-24 | 2026-06-28 | 5 | COMPLETED | 3.2 | 1900-01-05 | 2026-06-28 | Completed
| 3.4 Prepare encoded features and stratified split | Manvith Mogaveera | 2026-06-27 | 2026-06-30 | 4 | COMPLETED | 3.2, 3.3 | 1900-01-06 | 2026-06-30 | Completed
| 3.5 Train Decision Tree and Random Forest | Manvith Mogaveera | 2026-06-30 | 2026-07-03 | 4 | COMPLETED | 3.4 | 1900-01-06 | 2026-07-03 | Completed
| 3.6 Train Extra Trees | Manvith Mogaveera | 2026-07-02 | 2026-07-04 | 3 | COMPLETED | 3.4 | 1900-01-04 | 2026-07-04 | Completed
| 3.7 Train XGBoost and LightGBM | Manvith Mogaveera | 2026-07-03 | 2026-07-07 | 5 | COMPLETED | 3.4 | 1900-01-07 | 2026-07-07 | Completed
| 3.8 Train CatBoost | Manvith Mogaveera | 2026-07-05 | 2026-07-08 | 4 | COMPLETED | 3.4 | 1900-01-06 | 2026-07-08 | Completed
| 3.9 Evaluate accuracy, precision, recall and F1 | Manvith Mogaveera | 2026-07-08 | 2026-07-10 | 3 | COMPLETED | 3.5-3.8 | 1900-01-05 | 2026-07-10 | Completed
| 3.10 Confusion matrix and model comparison | Manvith Mogaveera | 2026-07-09 | 2026-07-11 | 3 | COMPLETED | 3.9 | 1900-01-04 | 2026-07-11 | Completed
| 3.11 Feature importance and model limitation analysis | Manvith Mogaveera | 2026-07-10 | 2026-07-12 | 3 | COMPLETED | 3.10 | 1900-01-04 | 2026-07-12 | Completed
| 3.12 Select best-performing model | Manvith Mogaveera | 2026-07-12 | 2026-07-13 | 2 | COMPLETED | 3.11 | 1900-01-02 | 2026-07-13 | Completed
| 3.13 Design CareerAI Streamlit dashboard | Manvith Mogaveera | 2026-07-10 | 2026-07-13 | 4 | COMPLETED | 2.5 | 1900-01-05 | 2026-07-13 | Completed
| 3.14 Build user profile prediction form | Manvith Mogaveera | 2026-07-12 | 2026-07-16 | 5 | COMPLETED | 3.13 | 1900-01-07 | 2026-07-16 | Completed
| 3.15 Build prediction result and career display | Manvith Mogaveera | 2026-07-15 | 2026-07-18 | 4 | COMPLETED | 3.12, 3.14 | 1900-01-06 | 2026-07-18 | Completed
| 3.16 Build EDA and model comparison dashboard | Manvith Mogaveera | 2026-07-16 | 2026-07-19 | 4 | COMPLETED | 3.10, 3.13 | 1900-01-05 | 2026-07-19 | Completed
| 3.17 Map career roles to required skills | Manvith Mogaveera | 2026-07-17 | 2026-07-20 | 4 | COMPLETED | 3.12 | 1900-01-05 | 2026-07-20 | Completed
| 3.18 Create career-specific course roadmaps | Manvith Mogaveera | 2026-07-19 | 2026-07-23 | 5 | COMPLETED | 3.17 | 1900-01-07 | 2026-07-23 | Completed
| 3.19 Integrate course recommendation module | Manvith Mogaveera | 2026-07-22 | 2026-07-24 | 3 | COMPLETED | 3.15, 3.18 | 1900-01-04 | 2026-07-24 | Completed
4 Testing | [10 empty] | COMPLETED | 1 | Completed
| 4.1 Test dataset loading and preprocessing | Manvith Mogaveera | 2026-07-24 | 2026-07-25 | 2 | COMPLETED | 3.19 | 1900-01-03 | 2026-07-25 | Completed
| 4.2 Test user input validation | Manvith Mogaveera | 2026-07-24 | 2026-07-26 | 3 | COMPLETED | 3.14 | 1900-01-03 | 2026-07-26 | Completed
| 4.3 Test prediction workflow | Manvith Mogaveera | 2026-07-25 | 2026-07-27 | 3 | COMPLETED | 4.1, 4.2 | 1900-01-04 | 2026-07-27 | Completed
| 4.4 Test course recommendation workflow | Manvith Mogaveera | 2026-07-26 | 2026-07-28 | 3 | COMPLETED | 4.3 | 1900-01-03 | 2026-07-28 | Completed
| 4.5 Validate model metrics and outputs | Manvith Mogaveera | 2026-07-27 | 2026-07-29 | 3 | COMPLETED | 3.12 | 1900-01-04 | 2026-07-29 | Completed
| 4.6 Test UI navigation and responsiveness | Manvith Mogaveera | 2026-07-28 | 2026-07-30 | 3 | COMPLETED | 4.3 | 1900-01-04 | 2026-07-30 | Completed
| 4.7 Fix defects and refine interface | Manvith Mogaveera | 2026-07-29 | 2026-07-31 | 3 | COMPLETED | 4.5, 4.6 | 1900-01-06 | 2026-07-31 | Completed
| 4.8 Prepare test report | Manvith Mogaveera | 2026-07-30 | 2026-07-31 | 2 | COMPLETED | 4.7 | 1900-01-03 | 2026-07-31 | Completed
5 Deployment | [10 empty] | COMPLETED | 1 | Completed
| 5.1 Prepare requirements.txt and project structure | Manvith Mogaveera | 2026-08-01 | 2026-08-02 | 2 | COMPLETED | 4.8 | 1900-01-03 | 2026-08-02 | Completed
| 5.2 Configure Streamlit application | Manvith Mogaveera | 2026-08-02 | 2026-08-04 | 3 | COMPLETED | 5.1 | 1900-01-04 | 2026-08-04 | Completed
| 5.3 Run final deployment/demo build | Manvith Mogaveera | 2026-08-04 | 2026-08-07 | 4 | COMPLETED | 5.2 | 1900-01-05 | 2026-08-07 | Completed
6 Documentation | [10 empty] | COMPLETED | 1 | Completed
| 6.1 Maintain weekly project documentation | Manvith Mogaveera | 2026-06-12 | 2026-08-07 | 57 | COMPLETED |  | 1900-01-09 | 2026-08-07 | Completed
| 6.2 Prepare README and user guide | Manvith Mogaveera | 2026-08-05 | 2026-08-08 | 4 | COMPLETED | 5.3 | 1900-01-04 | 2026-08-08 | Completed
| 6.3 Prepare final technical report | Manvith Mogaveera | 2026-08-06 | 2026-08-10 | 5 | COMPLETED | 5.3 | 1900-01-07 | 2026-08-10 | Completed
7 Closure | [10 empty] | COMPLETED | 1 | Completed
| 7.1 Final project review and corrections | Manvith Mogaveera | 2026-08-08 | 2026-08-10 | 3 | COMPLETED | 6.2, 6.3 | 1900-01-04 | 2026-08-10 | Completed
| 7.2 Prepare final presentation/demo | Manvith Mogaveera | 2026-08-09 | 2026-08-11 | 3 | COMPLETED | 7.1 | 1900-01-04 | 2026-08-11 | Completed
| 7.3 Final handover and project closure | Manvith Mogaveera | 2026-08-12 | 2026-08-22 | 1 | COMPLETED | 7.2 | 1900-01-02 | 2026-08-22 | Completed
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1