## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 0 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | CareerAI – AI-Based Career Prediction & Learning Recommendation System |  | Project Id: | GPI-CAR-AI-001 | Project Manager: | Harshada Topale |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 0 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1.0 |  | Last Updated date: | 2026-08-22 | Project Team Lead: | Manvith Mogaveera |  |  | Dependency | 0 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 0 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
Risk | The supplied dataset may have weak predictive signal for the 12 Suggested Job Role classes, resulting in low model accuracy. | Low predictive performance may limit the usefulness of the career prediction output. | Report model performance honestly; compare multiple classifiers; analyse feature relevance; document dataset limitations; avoid unsupported accuracy claims. | Manvith Mogaveera | High | 16 | Open |  | Risk
Risk | Incorrect handling or interpretation of categorical and numerical features may reduce model performance. | Poor preprocessing can produce unreliable model evaluation and predictions. | Validate data types, missing values and encoding; use a consistent preprocessing pipeline for training and prediction. | Manvith Mogaveera | High | 12 | Open |  | Assumption
Risk | Python package or library version conflicts may prevent the ML application from running correctly. | Development, testing or demonstration may be delayed. | Maintain a requirements.txt file, use a controlled Python environment and test the application before demonstrations. | Manvith Mogaveera | Moderate | 9 | Open |  | Issue
Risk | Limited local computing resources may increase training time for ensemble models. | Model experimentation and development could take longer than planned. | Use efficient tree-based configurations, CPU-compatible models and avoid unnecessarily large hyperparameter searches. | Manvith Mogaveera | Moderate | 8 | Open |  | Dependency
Risk | Users may interpret the predicted career role as a guaranteed or definitive career choice. | The application could be misunderstood as a professional career assessment. | Clearly label predictions as guidance, show model limitations and provide learning recommendations rather than placement guarantees. | Manvith Mogaveera | Moderate | 6 | Open
Assumption | The teacher-provided PS2_Dataset.csv will remain available and usable for the project. | If the dataset becomes unavailable or changes unexpectedly, model development may be affected. | Keep a controlled project copy and document the dataset version used for the final model. | Manvith Mogaveera | High |  | Open |  | Open
Assumption | Python and required open-source/free libraries can be installed on the development machine. | The complete ML and Streamlit workflow depends on these tools. | Maintain a requirements.txt file and document installation steps. | Manvith Mogaveera | Moderate |  | Open |  | Closed
Issue | Current evaluation of the supplied dataset is close to random-chance performance for the 12 career classes. | The current model may not provide sufficiently reliable career-role separation. | Investigate feature quality and label relevance, compare alternative models, document the limitation and recommend better career-specific training data for future scope. | Manvith Mogaveera | Critical |  | Open
Dependency | The project depends on the official GPI problem statement, requirement-elicitation inputs and project schedule. | Changes or delays in approved requirements or schedule may affect implementation and submission. | Track requirement and schedule changes during weekly reviews and update project documentation when formally approved. | Manvith Mogaveera | High |  | Open |  | Critical
Dependency | The project depends on availability of the GPI Project Sponsor, Project Manager and relevant stakeholders for requirement clarification and reviews. | Delayed clarification can delay development or cause rework. | Raise clarification items during requirement and weekly meetings and record decisions in project documentation. | Manvith Mogaveera | Moderate |  | Open |  | High
Moderate
Low
Negligible